## Auto CW
Date | Task | User | IT | Scenario | Result
4/1 | Material Prequal Workflow - Auto C/W Pilot-run | 郭冠霖 | PreQual: 翁毓謙, Workflow: 許哲涵, 耿少宏 | 1. PR on-tool monitor: Prequal sys. Get new batch => Manually reproduce w/ old batch. 2. Register new Workflow: Prequal sys. send job to Workflow => Pass 3. Workflow trigger CWCP to create new CW order => Pass 4. Workflow ask Flag to get PR used-time => Pass 5. Workflow ask to do inhibition => No need in this test 6. Workflow ask to trigger CW => Pass, 7. CWCP feedback 控片出機 => Fail, user manually cancel the CWCP - Workflow send timeout mail => Pass # Issues: 1. 未設定禁用, Workflow仍會送出禁用成功mail a. 不該送出 b. 即使送出, 信中須告知"By-Pass"禁用 2. | 7 Pass 1 Fail

## Issues
Initial Date | Function | Type | Task | Sponsor | Status
4/1 | Auto-CW | Bug | 未設定禁用, Workflow仍會送出禁用成功mail a. 不該送出 b. 即使送出, 信中須告知"By-Pass"禁用
| Auto-CW | URD Change | Extend time-out settings when ask Flag PR used-time |  | Short-term:
|  | Bug | Dao

## Tasks
Initial Date | Function | Type | Task | Sponsor | Status | Follow-ups | Action
4/15 |  | System Issue | FacTagData Loader stopped from 3/19 | MQSI\林聖凱 | AR | Need to create FacTagData monitor. 1. Dao data loader 失敗預防機制 2. AP 端預防機制 | 聖凱 restarted loader on 4/15
4/15 |  | AR | FacTagData monitor. 1. Dao data loader 失敗預防機制 2. AP 端預防機制 | 1. MQSI\林聖凱 2. IEAD\翁毓謙 | Open
4/15 |  | System Issue | F18P3 Lorry PreQual從4/12開始未啟動 |  | AR | Need to create data quality monitor. 1. Bluebook資料完整度 2. 廠務換料 vs. ees-data quality 3. AP端預防機制 | Bluebook 2.0改版,影響ees-dao未能拿到F18P3換料紀錄
4/15 |  | AR | Need to create data quality monitor. 1. Bluebook資料完整度 2. 廠務換料 vs. ees-data quality 3. AP端預防機制 | 1. MQSI\陳建良 2. MQSI\陳建良 3. IEAD\翁毓謙 | Open