## Auto CW
Date | Task | User | IT | Scenario | Result
4/1 | Material Prequal Workflow - Auto C/W Pilot-run | 郭冠霖 | PreQual: 翁毓謙, Workflow: 許哲涵, 耿少宏 | 1. PR on-tool monitor: Prequal sys. Get new batch => Manually reproduce w/ old batch. 2. Register new Workflow: Prequal sys. send job to Workflow => Pass 3. Workflow trigger CWCP to create new CW order => Pass 4. Workflow ask Flag to get PR used-time => Pass 5. Workflow ask to do inhibition => No need in this test 6. Workflow ask to trigger CW => Pass, 7. CWCP feedback 控片出機 => Fail, user manually cancel the CWCP - Workflow send timeout mail => Pass # Issues: 1. 未設定禁用, Workflow仍會送出禁用成功mail a. 不該送出 b. 即使送出, 信中須告知"By-Pass"禁用 2. | 7 Pass 1 Fail

## Issues
Initial Date | Function | Type | Task | Sponsor | Status | Follow-ups | Action
4/1 | Auto-CW | Bug | 未設定禁用, Workflow仍會送出禁用成功mail a. 不該送出 b. 即使送出, 信中須告知"By-Pass"禁用
4/1 | Auto-CW | URD Change | Extend time-out settings when ask Flag PR used-time |  | Short-term:
4/15 | FHM | System Issue | FacTagData Loader stopped from 3/19 | MQSI\林聖凱 | Close w/ AR | Need to create FacTagData monitor. 1. Dao data loader 失敗預防機制 2. AP 端預防機制 | 聖凱 restarted loader on 4/15
4/15 | FHM | AR | FacTagData monitor. 1. Dao data loader 失敗預防機制 2. AP 端預防機制 | 1. MQSI\林聖凱 2. IEAD\翁毓謙 | Open
4/15 | FHM | System Issue | F18P3 Lorry PreQual從4/12開始未啟動 | 1. MQSI\林聖凱 2. IEAD\翁毓謙 | Close w/ AR | Need to create data quality monitor. 1. Bluebook資料完整度 2. 廠務換料 vs. ees-data quality 3. AP端預防機制 | Bluebook 2.0改版,影響ees-dao未能拿到F18P3換料紀錄
4/15 | FHM | AR | Need to create data quality monitor. 1. Bluebook資料完整度 2. 廠務換料 vs. ees-data quality 3. AP端預防機制 | 1. MQSI\陳建良 2. MQSI\陳建良 3. IEAD\翁毓謙 | Open
4/23 | Auto-CW | Bug | <F15B> Workflow call Inhibition回來的resultMemo太長,發生exception | 耿少宏 | Action: 回Teams請問少宏 1. "Bad Input Param" 是否跟送進去的內容有關 ? 2. Bug fix schedule.
4/22 | FHM | Bug | <F14B> Fail to get Slurry drum_actl_dlvr_time/used_time - L146171C: P5/6 no data - L146182 | User: 王來彥 IT: 陳彥勳/陳建良

## Tasks
Initial Date | Function | Type | Task | Sponsor | Status | Follow-ups | Action
| Pre-Qual Summary |  | F18 query no data | YuChien | Open | 1. Service 轉頭 2. 確認deploy status, 3. 確認WAF end-point status | 1. Code merge and rebuild code w/ vs-2010. 2. Deploy to F18 for pilot run
| Dashboard | Impl. | <GUI> Pre-Qual. Dashboard - L3. 1. List all new batch pre-qual status 2. One-cliek to switch background theme 3. "Filter" w/ key columns. 4. raw data page. | 宥縈
| Dashboard | Impl. | <Srvc.> Data service to query Pre-Qual. Summary data. | Penny |  | select * from ppmsdm.rawmat_pre_batch_status
| Dashboard | Impl.
| Dashboard | Impl. | <GUI> Common function to show Perf. Rpt. - Get report content from SAO. | Penny |  |  | Input: case-id, data subject, Output: sao content
| Dashboard | Impl. | <GUI> Function linkage to show Perf. Rpt. - SPC, Defect, FAC | 宥縈
| Dashboard | Impl. | <GUI> Pre-Qual. Dashboard - L2. 1. Department level dashboard 2. One-cliek to switch background theme 3. | 宥縈
| Dashboard | Impl. | <GUI> Pre-Qual. Dashboard - L1. 1. FAB level dashboard 2. One-cliek to switch background theme 3. | 宥縈