## Auto CW
Date | Task | User | IT | Scenario | Result
4/1 | Material Prequal Workflow - Auto C/W Pilot-run | 郭冠霖 | PreQual: 翁毓謙, Workflow: 許哲涵, 耿少宏 | 1. PR on-tool monitor: Prequal sys. Get new batch => Manually reproduce w/ old batch. 2. Register new Workflow: Prequal sys. send job to Workflow => Pass 3. Workflow trigger CWCP to create new CW order => Pass 4. Workflow ask Flag to get PR used-time => Pass 5. Workflow ask to do inhibition => No need in this test 6. Workflow ask to trigger CW => Pass, 7. CWCP feedback 控片出機 => Fail, user manually cancel the CWCP - Workflow send timeout mail => Pass # Issues: 1. 未設定禁用, Workflow仍會送出禁用成功mail a. 不該送出 b. 即使送出, 信中須告知"By-Pass"禁用 2. | 7 Pass 1 Fail

## Tasks
Initial Date | Function | Type | Task | Sponsor | Status
4/1 | Auto-CW | Bug | 未設定禁用, Workflow仍會送出禁用成功mail a. 不該送出 b. 即使送出, 信中須告知"By-Pass"禁用
| Auto-CW | URD Change | Extend time-out settings when ask Flag PR used-time |  | Short-term: